## Wx
PROJECT REPORT
Group | GFA26SE94 — VISTA (FA26SE183)
Week | 21/10/2026–25/10/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Review 2 scope + Registration | Lê Nguyễn Quang Đức | In Progress | Registration v1.2, BM03, four workflow owners; submission ID FA26SE183.
2 | School robot allocation WF-01 | Lê Nguyễn Quang Đức | In Progress | School Admin entitlement and atomic classroom allocation; verified source docs.
3 | Learning assignment WF-02 | Trần Tiến Đạt | In Progress | Course offerings, classroom assignments, program version and submissions; e2e unverified.
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | State and ERD consistency not signed off | Trần Tiến Đạt / Phạm Viết Lợi | Pending | Audit enum transitions / FK uniqueness vs diagrams.
2 | BM02 tag and CI evidence missing | Lê Nguyễn Quang Đức | Pending | Do not claim complete before tag and raw AI findings.
3 | Physical robot E2E not verified | Vũ Anh Tuấn | Pending | Clearly separate schematic experiment from robot execution.
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Validate SRS/SDD vs repo and migrations | Lê Nguyễn Quang Đức | Before Review 2 | Cross-check FR / APIs / states / data.
2 | Audit robot runtime and exceptions | Vũ Anh Tuấn | Before Review 2 | Run safe tests and record evidence, no hardware assumptions.
3 | Update Activity/State diagrams | Trần Tiến Đạt | Before Review 2 | Source code guided diagrams in PlantUML.
4 | Review Logical ERD + SQL constraints | Phạm Viết Lợi | Before Review 2 | FK/nullable/unique; 76-table Supabase live reference.
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Use repository tag review-2 only after docs/tests pass | Lê Nguyễn Quang Đức |  | BM02 standard prompt must run on frozen tagged commit; preserve findings.