## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
0 | Student/Teacher Login | Identity | Simple | Supabase JWT authentication; role-based navigation; auth guard. | Iteration 1 | Pending
1 | School-scoped Authorization | Identity | Complex | Organization membership and scope checks; deny cross-school requests. | Iteration 1 | Pending
2 | School Admin: Classroom Management | School Admin | Medium | List and manage organization classrooms with authorized memberships. | Iteration 1 | Pending
3 | Robot Entitlement Management | Robot Resource | Complex | Verify organization entitlement for available robots. | Iteration 1 | Pending
4 | Classroom Robot Allocation (WF-01) | Robot Resource | Complex | One allocation per classroom; replacing robot is atomic; no motion/reservation. | Iteration 1 | Pending
5 | Course and Lesson Management | Curriculum | Medium | Instructor manages learning courses and lessons within allowed scope. | Iteration 1 | Pending
6 | Course Offering / Classroom Delivery | Learning | Complex | Link course delivery to class and teacher/student membership. | Iteration 1 | Pending
7 | Assignment Publishing (WF-02) | Learning | Complex | Teacher publishes classroom assignment; visibility restricted to class. | Iteration 1 | Pending
8 | Blockly Program / Program Version | Programming | Complex | Student builds learning program with immutable program versions. | Iteration 2 | Pending
9 | Submission and Attempts (WF-02) | Assessment | Complex | Student submits within assigned class; store submission and attempts. | Iteration 1 | Pending
10 | Schematic Experiment Preview (WF-03) | Experiment | Complex | Create pending schematic preview; no physical execution via Education API. | Iteration 2 | Pending
11 | Experiment Evidence and Events | Experiment | Medium | Read own experiment result, events and artifacts; verify scope. | Iteration 2 | Pending
12 | Teacher Assessment (WF-04) | Assessment | Complex | Teacher reviews submitted work, stores assessment and feedback. | Iteration 2 | Pending
13 | Student Reflection and Feedback | Assessment | Medium | Student accesses feedback and records permitted reflection. | Iteration 2 | Pending
14 | CI & Documentation Traceability | Quality | Complex | Tests, build, schema checks; repo diagrams and review-2 documentation. | Iteration 1 | Pending
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
| complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | WF-03 physical path not integrated | End-to-end hardware claim unsupported | High | Vũ Anh Tuấn |  |  | Open | Education API supports schematic pending requests; confirm scope
2 | State diagrams use proposed states | BM02 may detect mismatch with implementation | High | Trần Tiến Đạt |  |  | Open | Rebuild from enums, controllers and DB constraints
3 | ERD optionality/cardinality requires constraints | Data review could flag invalid relations | High | Phạm Viết Lợi |  |  | Open | Compare uniqueness/nullability with migrations
4 | SRS requirements not fully code-traced | AI Self Review scope/design mismatch | High | Lê Nguyễn Quang Đức |  |  | Open | Build FR → route → DB → tests matrix
5 | Review-2 tag & BM02 not yet finalized | Official submission incomplete | High | Lê Nguyễn Quang Đức |  |  | Open | Tag only after docs, test and CI verified
6 | Robot runtime safety evidence incomplete | Defense demo risk | Medium | Vũ Anh Tuấn |  |  | Open | Keep safety claims qualified; test without hardware
7 | CI workflow outcomes unverified | No confirmed green runs | Medium | Lê Nguyễn Quang Đức |  |  | Open | CI steps exist; check Actions result and remaining workflows

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Verification | Test execution | QA pending | No confirmed defect list; do not fabricate results | Assigned after CI | Pending | Record only reproduced defects with logs

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
| Which ID is the official project code? | Leader | High | Open | Latest confirmed: FA26SE183; group GFA26SE94. Prefix per school guide SWP490; check subject admin if SEP490 required.
| Does WF-03 include physical robot motion? | Team | High | Open | No end-to-end physical invocation proven through Education API; schematic request only.
| Which diagrams must be in repository? | Team | High | Open | System Overview, Logical ERD, State Machines, 4 Activity workflows as Mermaid or PlantUML.
| Are all required workflow states implemented? | Team | High | Open | Verify from code, do not use aesthetic placeholder states.
| When is BM02 generated? | Leader | High | Open | After review-2 Git tag. Keep raw AI findings unchanged.
| When is BM04 submitted? | Leader | Medium | Open | Within 3 business days after Review 2, subject to faculty confirmation.
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open